## Sheet1
REQUIREMENTS TRACEABILITY MATRIX
Project Name |  | The Thompson Project |  |  | Date |  | 2022-11-21
Project Group |  | Never Gonna Give UPS |  |  | Document Number |  | 1.3
Project Manager |  |  |  |  | Project Owner/Client |  | Armond Thompson
ID Number | Requirement Name | Source | Date Received | Status | Assigned To | Acceptance Criteria | Tested By and Date | Accepted By and Date
1.1 | AddUser | Black Hat Specs | 2022-08-31 | Complete | ZSG | User added to user list | All 10/24/22 | All 10/24/22
1.2 | EditUser | Black Hat Specs | 2022-08-31 | Complete | ZSG | User privileges changed | All 10/24/22 | All 10/24/22
1.3 | DeleteUser | Black Hat Specs | 2022-08-31 | Complete | ZSG | User removed from user list. | All 10/24/22 | All 10/24/22
2.1 | AddAdmin | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin added to user list | All 10/24/22 | All 10/24/22
2.2 | EditAdmin | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin privileges changed. | All 10/24/22 | All 10/24/22
2.3 | DeleteAdmin | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin removed from user list | All 10/24/22 | All 10/24/22
3.1 | AddVolunteer | Black Hat Specs | 2022-08-31 | Complete | TALB, CW | Volunteer form submitted. Volunteer added to user list | All 10/24/22 | All 10/24/22
3.2 | EditVolunteer | Black Hat Specs | 2022-08-31 | Complete | TALB, CW | Volunteer form submitted. Volunteer changed in user list. | All 10/24/22 | All 10/24/22
3.3 | DeleteVolunteer | Black Hat Specs | 2022-08-31 | Complete | TALB, CW | Volunteer deleted from user list. | All 10/24/22 | All 10/24/22
4 | AllowLogIn | Black Hat Specs | 2022-08-31 | Complete | ZSG | From sign in page user can access account. | All 10/24/22 | All 10/24/22
5 | LogInPrivileges | Black Hat Specs | 2022-08-31 | Complete | ZSG | Separation of account accesses | All 10/24/22 | All 10/24/22
6.1 | CreateNewsletter | Black Hat Specs | 2022-08-31 | Complete | CW | Newletter created, can subscribe | 2022-11-09 | 2022-11-09
6.2 | EditNewsletter | Black Hat Specs | 2022-08-31 | Complete | CW | Plugin allows edits | 2022-11-09 | 2022-11-09
6.3 | DeleteNewsletter | Black Hat Specs | 2022-08-31 | Complete | CW | Can unsubscribe through email | 2022-11-09 | 2022-11-09
7.1 | CreateGrant | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin can create grant | ZSG, 10/31/2022 | N/A
7.2 | EditGrant | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin can edit grant | ZSG, 10/31/2022 | N/A
7.3 | DeleteGrant | Black Hat Specs | 2022-08-31 | Complete | ZSG | Admin can delete grant | ZSG, 10/31/2022 | N/A
8.1 | AddCalendarEvent | Black Hat Specs | 2022-08-31 | Complete | DM | Admin can add new events. | All 10/24/22 | All 10/24/22
8.2 | EditCalendarEvent | Black Hat Specs | 2022-08-31 | Complete | DM | Admin can update and make changes. | All 10/24/22 | All 10/24/22
8.3 | DeleteCalendarEvent | Black Hat Specs | 2022-08-31 | Complete | DM | Admin can delete past events. | All 10/24/22 | All 10/24/22
9.1 | CalendarPage | Black Hat Specs | 2022-08-31 | Complete | DM | Calender is visible on site. | All 10/24/22 | All 10/24/22
9.2 | UpdateCalendar | Black Hat Specs | 2022-08-31 | Complete | DM | New event are posted periodically. | All 10/24/22 | All 10/24/22
9.3 | DonatePage | Black Hat Specs | 2022-08-31 | Complete | ZSG | Visible on page. | All 10/24/22 | All 10/24/22
10.1 | DonateMap | Black Hat Specs | 2022-08-31 | Complete | ZSG | Visible on page. | N/A | N/A
11 | SearchBar | Black Hat Specs | 2022-08-31 | Complete | N/A | Finds content. | All 10/24/22 | All 10/24/22
12 | AccountLogIn | Black Hat Specs | 2022-08-31 | Complete | ZSG | User can log in | All 10/24/22 | All 10/24/22
13 | AddSearchBar | Black Hat Specs | 2022-08-31 | Complete | N/A | Visible on page. | All 10/24/22 | All 10/24/22
14.1 | EditPayments | Black Hat Specs | 2022-08-31 | Complete | N/A | User can adjust their donations. | All 10/24/22 | All 10/24/22
14.2 | DeletePayments | Black Hat Specs | 2022-08-31 | Complete | N/A | Payments can be removed by admin. | All 10/24/22 | All 10/24/22
15.1 | AddTestimonial | Black Hat Specs | 2022-08-31 | Complete | DM | Users can leave testimonial on site. | All 11/13/2022 | All 11/13/2022
15.2 | EditTestimonial | Black Hat Specs | 2022-08-31 | Complete | DM | User can update their testimonial. | All 11/13/2022 | All 11/13/2022
15.3 | DeleteTestimonial | Black Hat Specs | 2022-08-31 | Complete | DM | User and admin can delete their testimonial. | All 11/13/2022 | All 11/13/2022
16.1 | AddResource | Black Hat Specs | 2022-08-31 | Complete | AML | User can access resources | All 11/13/2022 | All 11/13/2022
16.2 | EditResource | Black Hat Specs | 2022-08-31 | Complete | AML | Admin can edit resources | All 11/13/2022 | All 11/13/2022
16.3 | DeleteResource | Black Hat Specs | 2022-08-31 | Complete | AML | Admin can delete resources | All 11/13/2022 | All 11/13/2022
17.1 | AddPhoto | Black Hat Specs | 2022-08-31 | Complete | DM, TALB, ZSC | Visible on page. | All 10/24/22 | All 10/24/22
17.2 | EditPhoto | Black Hat Specs | 2022-08-31 | Complete | DM, TALB, ZSC | Will be changed periodially | All 10/24/22 | All 10/24/22
17.3 | DeletePhoto | Black Hat Specs | 2022-08-31 | Complete | DM, TALB, ZSC | Can be removed. | All 10/24/22 | All 10/24/22
18.1 | AddAccount | Black Hat Specs | 2022-08-31 | Complete | ZSG | Accounts can be added to user list | All 10/24/22 | All 10/24/22
18.2 | EditAccount | Black Hat Specs | 2022-08-31 | Complete | ZSG | Accounts can have status changed in user list | All 10/24/22 | All 10/24/22
18.3 | DeleteAccount | Black Hat Specs | 2022-08-31 | Complete | ZSG | Accounts can be removed from user list | All 10/24/22 | All 10/24/22
19.1 | AddContactInfo | Black Hat Specs | 2022-08-31 | Complete | AML, CW | User can submit contact info | All 10/24/22 | All 10/24/22
19.2 | EditContactInfo | Black Hat Specs | 2022-08-31 | Complete | AML, CW | Admin can access/ change contact info | All 10/24/22 | All 10/24/22
19.3 | DeleteContactInfo | Black Hat Specs | 2022-08-31 | Complete | AML, CW | Admin can access/delete contact info | All 10/24/22 | All 10/24/22
20.1 | AddAttendees | Black Hat Specs | 2022-08-31 | Complete | CW | User can indicate they are attending | All 11/13/2022 | All 11/13/2022
20.2 | EditAttendees | Black Hat Specs | 2022-08-31 | Complete | CW | Admin can edit attendees | All 11/13/2022 | All 11/13/2022
20.3 | DeleteAttendees | Black Hat Specs | 2022-08-31 | Complete | CW | Admin can delete attendees | All 11/13/2022 | All 11/13/2022
21 | AllowBackup | Black Hat Specs | 2022-08-31 | Complete | ZSG | Website data is backed-up regularly | All 10/24/22 | All 10/24/22
22 | AllowRecovery | Black Hat Specs | 2022-08-31 | Complete | ZSG | Website data can be recovered at any time | All 10/24/22 | All 10/24/22
23.1 | CreatePhysicalDonation | Black Hat Specs | 2022-08-31 | Incomplete | N/A | Admin can create physical donation | N/A | N/A
23.2 | EditPhysicalDonation | Black Hat Specs | 2022-08-31 | Incomplete | N/A | Admin can edit physical donation | N/A | N/A
23.3 | DeletePhysicalDonation | Black Hat Specs | 2022-08-31 | Incomplete | N/A | Admin can delete physical donation | N/A | N/A
24.1 | CreateDonorList | Black Hat Specs | 2022-08-31 | Incomplete | TB | Admin can create a list of donations received | N/A | N/A
24.2 | EditDonorList | Black Hat Specs | 2022-08-31 | Incomplete | TB | Admin can donate a list of donations received | N/A | N/A
24.3 | DeleteDonorList | Black Hat Specs | 2022-08-31 | Incomplete | TB | Admin can delete a list of donations received. | N/A | N/A
25.1 | CreateVolunteerList | Black Hat Specs | 2022-08-31 | Complete | TB, CW | Admin can create a list of volunteers | All 11/16/2022 | All 11/16/2022
25.2 | EditVolunteerList | Black Hat Specs | 2022-08-31 | Complete | TB, CW | Admin can edit a list of volunteers | All 11/16/2022 | All 11/16/2022
25.3 | DeleteVolunteerList | Black Hat Specs | 2022-08-31 | Complete | TB, CW | Admin can delete a list of volunteers | All 11/16/2022 | All 11/16/2022
26.1 | CreateAboutUs | Tan Tabletop Specs | 2022-08-31 | Complete | ZSG | AboutUs text can be added | All 10/24/2022 | All 10/24/2022
26.2 | EditAbout Us | Tan Tabletop Specs | 2022-08-31 | Complete | ZSG | AboutUs text can be edited | All 10/24/2022 | All 10/24/2022
26.3 | DeleteAbout US | Tan Tabletop Specs | 2022-08-31 | Complete | ZSG | AboutUs text can be removed. | All 10/24/2022 | All 10/24/2022
27 | VolunteerApplication |  |  | Complete | TALB | Provides enough information for a background check | All 10/24/22 | All 10/24/22 | NEW
28 | TitleIXTraining |  |  | Complete | TALB | Links to training | All 10/24/22 | All 10/24/22
29.1 | EventSortDay |  |  | Complete | DM | Can sort by day | All 10/24/22 | All 10/24/22
29.2 | EventSortMonth |  |  | Complete | DM | Can sort by month | All 10/24/22 | All 10/24/22
29.3 | EventSortList |  |  | Complete | DM | Can sort into a full list | All 10/24/22 | All 10/24/22
29.4 | EventSearchButton |  |  | Complete | DM | Submits search bar information | All 10/24/22 | All 10/24/22
29.5 | EventSearchBar |  |  | Complete | DM | allows for textable information in the bar | All 10/24/22 | All 10/24/22

## _56F9DC9755BA473782653E2940F9 (hidden)
Sm4k3TRUFU6K45Gtl5eyCZfCD5-ZzlROnMV3_1_ZXoVUQ0JZRlVXWVhPSFFRT0MwQU9RR0Q2VzJMWSQlQCN0PWcu
Form1
{c499af3d-6b44-4b78-806b-a71d391c38ad}